## Cover Page
BIM EXECUTION PLAN (BEP)
ISO 19650-2 Pre-Contract BEP
Project Name | Project Name
Project Number | Project Number
Client Name | Client Name
Project Address | Enter address here Address Line 2
Issue Date | 2026-03-14
Bep Revision | P01
Bep Status | S3
Project Stage | 0 — Strategic Definition
Bep Preset | UK_GOV
Preset Description | UK Government Soft Landings — public sector, full ISO 19650
Project Description
Site Reference
Project Type | New Build
Procurement Route | Design and Build
Generated: 2026-03-14 19:06

## Project Team
Role | Code | Discipline | Contact | Company | Email
Lead Appointed Party | A | Architect
Architect | A | Architect
Client/Employer | K | Client Representative
Contractor | W | Contractor

## Goals & BIM Uses
Primary Goals
ISO 19650 compliant information management
Coordinated 3D model for clash detection
Automated asset tagging (STING ISO tags)
Government Soft Landings (GSL) compliance
Digital twin readiness for operational phase
COBie V2.4 data drop for FM handover
Quantity extraction for cost management
Bim Uses
use: Design Authoring ¦ stage: All ¦ responsible: As per RACI

## Roles & Responsibilities
Information Manager
| Role | Information Manager (ISO 19650)
| Raci | Accountable
| Responsibilities | [ "Manage the CDE and information workflows", "Coordinate information exchange milestones", "Validate suitability codes and approvals", "Maintain the BEP and MIDP", "Conduct information model audits" ]
Bim Coordinator
| Role | BIM Coordinator
| Raci | Responsible
| Responsibilities | [ "Federate discipline models", "Run clash detection and resolution", "Maintain STING tag compliance", "Generate coordination reports", "Manage model origin and shared coordinates" ]
Task Team Members
| Role | Task Team Members
| Raci | Responsible
| Responsibilities | [ "Author discipline-specific models", "Apply STING tags to all elements", "Follow naming conventions and LOD requirements", "Issue models with correct suitability codes", "Respond to coordination issues and RFIs" ]

## Process Design
Coordination Workflow
1. Each task team authors discipline model in Revit
2. STING AutoTag applied (DISC-LOC-ZONE-LVL-SYS-FUNC-PROD-SEQ)
3. Models issued to CDE SHARED container with suitability code
4. BIM Coordinator federates and runs clash detection
5. Issues raised and tracked in STING Issue Tracker
6. Resolved models re-issued; clashes closed
7. Information Manager authorizes to PUBLISHED container
Information Exchange Frequency | Fortnightly model drops aligned to MIDP milestones
Model Review Meetings | Weekly BIM coordination meetings

## MIDP
Stage | Stage Name | Target Date | Responsibility | Suitability | Deliverables
0 | Strategic Definition |  |  | S3 | Strategic brief Feasibility study
1 | Preparation and Briefing |  |  | S3 | Project brief EIR BEP
2 | Concept Design |  |  | S3 | Concept design models (LOD 200) Design option studies
3 | Spatial Coordination |  |  | S4 | Coordinated models (LOD 300) Clash reports Updated BEP
4 | Technical Design |  |  | S4 | Technical design models (LOD 350) Specifications DD2 COBie
5 | Manufacturing and Construction |  |  | S6 | Construction models (LOD 400) Shop drawings DD3 COBie
6 | Handover |  |  | S6 | As-built model (LOD 500) O&M manuals DD4 COBie FM Handover
7 | Use |  |  | S6 | AIM (Asset Information Model) Digital twin baseline

## Information Standard
Naming Convention | Project-Originator-Volume-Level-Type-Role-Class-Number
Naming Separator | -
Tag Format | - separated, 4-digit SEQ
Tag Segments | DISC-LOC-ZONE-LVL-SYS-FUNC-PROD-SEQ
Classification System | Uniclass 2015
Units
| Length | Millimeters
| Area | Square Meters
File Formats
| Native | Autodesk Revit (.rvt)
| Exchange | IFC 4 / IFC 2x3
| Drawings | PDF/A-1b
| Data | COBie V2.4 (XLSX)

## Software Platforms
Platform | Purpose | Version
Autodesk Revit 2025+ | BIM Authoring
StingTools | ISO 19650 Asset Tagging & BIM Management | V2.1
Navisworks Manage | Federated model review & clash detection
IFC 4 / IFC 2x3 | Open BIM data exchange

## Model Structure
Shared Coordinates | Project base point at site origin
Model Origin | Shared Coordinates aligned to survey grid
Federation Strategy | One model per discipline, federated in Navisworks
Workset Strategy | STING standard worksets (35 worksets per STING Template)

## CDE Workflow
Cde Platform | Autodesk Construction Cloud (ACC)
Containers
| WIP | Work In Progress — authoring environment
| SHARED | Shared — for coordination and review
| PUBLISHED | Published — approved for downstream use
| ARCHIVE | Archive — superseded or historical
Suitability Codes
| S0 | Work In Progress
| S1 | Fit for Coordination
| S2 | Fit for Information
| S3 | Fit for Review and Comment
| S4 | Fit for Stage Approval
| S5 | Fit for Manufacturing/Procurement
| S6 | Fit for PIM Authorization
| S7 | Fit for AIM Authorization
| CR | As-Constructed Record Document
| AB | Abandoned/Superseded
Revision Format | P01, P02... (Preliminary) → C01, C02... (Construction)

## Level of Info Need
Lod By Stage
| Stage 2 | LOD 200 — Approximate geometry, generic types
| Stage 3 | LOD 300 — Specific geometry, accurate dimensions
| Stage 4 | LOD 350 — Detailed geometry, connections, supports
| Stage 5 | LOD 400 — Fabrication-ready, shop drawings
| Stage 6 | LOD 500 — As-built, verified field conditions
Loi Requirements
| Stage 2 | Basic identity + STING DISC/LOC/ZONE tags
| Stage 3 | Full 8-segment ISO tags + system classification
| Stage 4 | Technical parameters (flow, power, pressure) + manufacturer
| Stage 5 | Serial numbers, installation dates, warranty
| Stage 6 | As-built verification, O&M data, COBie populated

## Clash Detection
Detection Tool | STING Clash Detection + Navisworks Manage
Tolerance Mm | 25
Clash Groups
test: MEP vs Structure ¦ priority: HIGH ¦ tolerance_mm: 25
test: HVAC vs Electrical ¦ priority: HIGH ¦ tolerance_mm: 50
test: Plumbing vs Structure ¦ priority: HIGH ¦ tolerance_mm: 25
test: Fire Protection vs All ¦ priority: CRITICAL ¦ tolerance_mm: 10
test: Ceiling clearance ¦ priority: MEDIUM ¦ tolerance_mm: 100
Resolution Workflow | Issue raised → Assigned → Resolved → Verified → Closed

## Quality Assurance
Model Audits
STING Validate Tags — ISO 19650 token compliance
STING Pre-Tag Audit — predict issues before tagging
STING Template Validation — 45-check BIM template audit
STING BEP Compliance — validate against BEP allowed codes
STING Completeness Dashboard — per-discipline RAG status
Tag Completeness Target | 95% of elements tagged with complete 8-segment ISO tags
Audit Frequency | Weekly automated audit + monthly manual review

## Security
Access Levels
Read-Only
Contributor
Reviewer
Approver
Admin
Model Protection | Workset-based access control + central model ownership
Classification | OFFICIAL

## Handover Requirements
Cobie Version | COBie V2.4 (UK)
Data Drops
drop: DD1 ¦ stage: End of Stage 2 ¦ content: Spatial data, room lists, basic types
drop: DD2 ¦ stage: End of Stage 3 ¦ content: Full asset register, system classifications
drop: DD3 ¦ stage: End of Stage 4 ¦ content: Technical data, manufacturer info, specifications
drop: DD4 ¦ stage: End of Stage 6 ¦ content: As-built data, serial numbers, warranty, O&M
Deliverables
Native Revit model (.rvt) with STING tags
IFC 4 export with STING property sets
COBie V2.4 spreadsheet (STING FM Handover)
Asset Register CSV (STING Tag Register Export)
Bill of Quantities XLSX (STING BOQ Export)
FM O&M Handover Manual (STING Handover Manual)

## Risk Register
Risk | Impact | Mitigation
Late model delivery | HIGH | MIDP milestone tracking in STING
Coordination clashes | HIGH | Weekly clash detection via STING
Incomplete asset data | MEDIUM | STING Completeness Dashboard + Pre-Tag Audit
Non-compliant naming | MEDIUM | STING Doc Naming Validator
Data loss/corruption | CRITICAL | Central model + backup schedule

## Allowed Codes
Allowed Disc
A
E
FLS
FP
G
LV
M
P
S
Allowed Loc
BLD1
BLD2
BLD3
EXT
Allowed Zone
Z01
Z02
Z03
Z04
Allowed Sys
ARC
COM
DCW
DHW
FLS
FP
GAS
GEN
HVAC
HWS
ICT
LV
NCL
RWD
SAN
SEC
STR