## Cover
KAMPALA UGANDA TEMPLE
Master Information Delivery Plan
The aggregated schedule of information deliverables for the project, compiled from the Task Information Delivery Plan of every appointed party.
Document reference | KUT-SMB-ZZ-ZZ-SC-Z-0001
Revision | P01
Status / suitability | A1 — Authorised for use
Prepared by | Symbion Consulting Group Studios (Information Manager)
Baselined | [FILL — date]
Last updated | [FILL — date]
Update frequency | Monthly, and at every data drop
How to use this workbook
Programme | Enter the appointment date here, once. Every calendar date in the workbook is calculated from it.
MIDP | The project register. One row per deliverable. Filter by discipline, stage or status. The Information Manager maintains this sheet.
TIDP-… | One Task Information Delivery Plan per appointed party, pre-filled with the deliverables already assigned to it. Confirm the dates, add anything your scope requires that is not listed, and return the sheet. TIDP-ALL carries the deliverables every party owes.
Summary | Counts by stage, discipline and delivery plan, calculated from the MIDP sheet. Nothing is typed here.
Drawing schedule | Indicative sheet counts by volume and role, for production planning.
Change log | What changed since the previous issue of this register, and why, including the references that were retired.
Lists | The permitted values behind the drop-down lists. Amend here to change the drop-downs.
Before this plan is baselined
The Originator column is deliberately empty. The originator code register has not been confirmed, and the container naming rule requires a code of a fixed length that is still to be agreed. Complete the Originator column only once the register is issued. Nothing on this project is to be numbered before that point.
Issued through the Common Data Environment. Uncontrolled when printed.

## Programme
Programme
Appointment date (M0) |  |  | ← the only date entered by hand. Everything else is calculated from it.
Stage durations are the Appointing Party Work Program: Phase 2 totals 11 months and Phase 3 totals 38 months, 49 in all, read in sequence.
Stage | From | To | Starts | Ends | Months
2.1 Basis of Design (Deliverable A) | M1 | M1 |  |  | 1
2.2 Developed Design (Deliverable B) | M2 | M4 |  |  | 3
2.3 Technical Design (Deliverable C) | M5 | M8 |  |  | 4
2.4 Tender action, negotiation and award | M9 | M11 |  |  | 3
2.5 Conformed set | M11 | M11 |  |  | 0
3.1 Construction administration | M12 | M43 |  |  | 32
3.2 FF&E installation | M44 | M47 |  |  | 4
3.3 Close-out (Deliverable D) | M48 | M49 |  |  | 2
Total |  |  |  |  | 49
Calendar dates are indicative until the appointment date is entered and the plan is rebaselined. A stage runs to the end of its final month, so a stage ending M8 ends on the last day of the eighth month after appointment.

## MIDP
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
Z-000 | Information Management |  | ZZ | BIM Execution Plan | Document | RP | Mobilisation | n/a | DOCX/PDF | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Baselined at mobilisation; reissued per stage
Z-001 | Information Management |  | ZZ | Master Information Delivery Plan | Schedule | SC | Mobilisation | n/a | XLSX | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Aggregated from all TIDPs; monthly and per drop
Z-002 | Information Management |  | ZZ | Project Delivery Playbook | Document | RP | Mobilisation | n/a | DOCX/PDF | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Reference RP-Z-0002
Z-003 | Information Management |  | ZZ | Responsibility matrix (RACI) | Schedule | SC | Mobilisation | n/a | XLSX | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Reference SC-Z-0002
Z-004 | Information Management |  | ZZ | Project template, family library and title blocks | Model | M3 | Mobilisation | n/a | RVT/RFA | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Coordinates, levels, grids, worksets, shared parameters bound
Z-005 | Information Management |  | ZZ | Originator code register | Schedule | SC | Mobilisation | n/a | XLSX | A1 | Published | 0 | 0 |  |  |  | Lead Appointed Party | TIDP-Z | Y | N | N |  | Required before any container is numbered; 3-character codes
Z-006 | All disciplines |  | ZZ | Task Information Delivery Plan (one per appointed party) | Schedule | SC | Mobilisation | n/a | XLSX | S3 | Shared | 0 | 0 |  |  |  | Task Team Managers | TIDP-ALL | N | N | N |  | Returned to the Information Manager; merged into this MIDP
Z-007 | Information Management |  | ZZ | Standards reconciliation schedule (BEP 4.1.3) | Schedule | SC | Mobilisation | n/a | XLSX/PDF | S3 | Shared | 0 | 8 |  |  |  | All disciplines | TIDP-Z | Y | N | N |  | Opened at mobilisation; closed before Stage 2.3
Z-008 | Information Management |  | ZZ | Shared coordinates seed model | Model | M3 | Mobilisation | n/a | RVT | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Survey point, project base point, true north, levels and grids
Z-009 | Information Management |  | ZZ | Level and grid register | Schedule | SC | Mobilisation | n/a | XLSX/PDF | A1 | Published | 0 | 0 |  |  |  | Lead Appointed Party | TIDP-Z | Y | N | N |  | Reference SC-Z-0003
Z-011 | Information Management |  | ZZ | Software and version register | Schedule | SC | Mobilisation | n/a | XLSX | A1 | Published | 0 | 0 |  |  |  | All parties | TIDP-Z | N | N | N |  | Revit 2025 locked project-wide
Z-012 | Information Management |  | ZZ | CDE folder structure and permission matrix | Document | RP | Mobilisation | n/a | PDF | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | ACC provisioned; seats confirmed for every party (E-01)
Z-013 | Information Management |  | ZZ | Information classification and access schedule | Document | RP | Mobilisation | n/a | PDF | A1 | Published | 0 | 0 |  |  |  | Appointing Party | TIDP-Z | Y | N | N |  | Restricted spaces and systems classified before modelling begins
Z-014 | Information Management |  | ZZ | Clash matrix and tolerance schedule | Document | RP | Mobilisation | n/a | PDF | S3 | Shared | 1 | 1 |  |  |  | MEP and structural leads | TIDP-Z | Y | N | N |  | Required before the first coordination cycle of Stage 2.2
Z-015 | Information Management |  | ZZ | IFC export configuration | Document | RP | Mobilisation | n/a | PDF/JSON | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Issued centrally
Z-016 | Information Management |  | ZZ | Shared parameter file | Document | RP | Mobilisation | n/a | TXT | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Central ownership
Z-017 | Information Management |  | ZZ | Capability and capacity assessment | Report | RP | Mobilisation | n/a | XLSX | S3 | Shared | 1 | 1 |  |  |  | Lead Appointed Party | TIDP-Z | N | N | N |  | ISO 19650-2; the Stage 0 test model is its practical form
Z-018 | Information Management |  | ZZ | Standards localisation note (Owner standards to Ugandan practice) | Document | RP | Mobilisation | n/a | DOCX/PDF | S3 | Shared | 0 | 1 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Reference RP-Z-0005; weeks 2–3 after the Owner standards are received
Z-019 | Information Management |  | ZZ | Stage 0 gate record (test model shared by every appointed party) | Report | RP | Mobilisation | n/a | PDF | S3 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | No discipline enters the fortnightly cycle before this
Z-020 | Information Management |  | ZZ | Monthly BIM status report (design stage) | Report | RP | Mobilisation | n/a | PDF | S2 | Shared | 1 | 11 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | KPIs per BEP 10.5
Z-021 | Information Management |  | ZZ | Kickoff induction record and BEP acknowledgement | Document | RP | Mobilisation | n/a | PDF | A1 | Published | 0 | 1 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Attendance and signed acknowledgement from every task team
Z-022 | Information Management |  | ZZ | Document Control Standard (reissued to P02 codes) | Document | RP | Mobilisation | n/a | DOCX/PDF | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | KUT-SMB-ZZ-ZZ-RP-Z-0003. Container naming, sheet number bands, revision, authorisation, transmittal, superseded/cancelled/replaced notices, number retirement
Z-024 | Information Management |  | ZZ | Drawing register, transmittal and notice templates | Document | TR | Mobilisation | n/a | XLSX/DOCX | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N
Z-010 | Information Management |  | ZZ | Federated coordination model | Model | M3 | 2.1 Deliverable A | 200 | NWC/NWD/IFC | S1 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | Y | Y | N |  | First federation; container M3-Z-0001
A-100 | Architecture |  | ZZ | Architectural model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | Architecture lead | TIDP-A | Y | Y | N |  | Massing and generic systems; rooms placed
A-101 | Architecture |  | ZZ | Deliverable A drawing set | Drawing | SH | 2.1 Deliverable A | 200 | PDF/DWG | S3 | Shared | 1 | 1 |  |  |  | Architecture lead | TIDP-A | N | N | N
S-100 | Structure |  | ZZ | Structural model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | Structural lead | TIDP-S | Y | Y | N |  | Indicative frame and foundations
M-100 | Mechanical |  | ZZ | Mechanical model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | MEP lead | TIDP-M | Y | Y | N |  | Plant space allocation, primary routes
E-100 | Electrical |  | ZZ | Electrical model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | MEP lead | TIDP-E | Y | Y | N |  | Generic equipment and main containment
P-100 | Public Health |  | ZZ | Plumbing and drainage model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | MEP lead | TIDP-P | Y | Y | N |  | Primary routes; font systems indicated
G-100 | Civil and Site |  | 00 | Site model and levels | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | Civil lead | TIDP-G | Y | Y | N |  | Site levels, access, drainage strategy; scope to confirm
Z-110 | Information Management |  | ZZ | Basis of design report | Document | RP | 2.1 Deliverable A | 200 | DOCX/PDF | S3 | Shared | 1 | 1 |  |  |  | Lead Appointed Party | TIDP-Z | N | N | N |  | Design intent
Z-111 | Information Management |  | ZZ | Area schedule reconciled to the brief | Schedule | SC | 2.1 Deliverable A | 200 | XLSX/PDF | S3 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Gate condition
Z-112 | Information Management |  | ZZ | Deliverable A gate pack and compliance report | Document | RP | 2.1 Deliverable A | 200 | PDF | S4 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Contents per Playbook Appendix B
Z-113 | Information Management |  | ZZ | Deliverable A Owner review set and comment close-out report | Document | RP | 2.1 Deliverable A | 200 | PDF | S3 | Shared | 1 | 2 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Comments closed before the gate
Z-114 | Information Management |  | ZZ | Baseline model-health report | Report | RP | 2.1 Deliverable A | 200 | PDF | S2 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | N | N | N
A-200 | Architecture |  | ZZ | Architectural model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | Architecture lead | TIDP-A | Y | Y | N |  | Real geometry, correctly located; no placeholder families
A-201 | Architecture |  | ZZ | General arrangement plans, sections and elevations (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | Architecture lead | TIDP-A | N | Y | N
A-202 | Architecture |  | ZZ | Door and window schedules | Schedule | SC | 2.2 Deliverable B | 300 | PDF/XLSX | S2 | Shared | 4 | 4 |  |  |  | Architecture lead | TIDP-A | N | N | N
A-203 | Architecture |  | ZZ | Room data sheets (key spaces) | Room data sheet | RD | 2.2 Deliverable B | 300 | PDF | S2 | Shared | 4 | 4 |  |  |  | Architecture lead | TIDP-A | N | N | N |  | Complete set at Deliverable C (A-302)
A-204 | Architecture |  | ZZ | Existing conditions and removals plan | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | Architecture lead | TIDP-A | N | N | N |  | Demolition classification is a manual task; BEP 10.4
S-200 | Structure |  | ZZ | Structural model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | Structural lead | TIDP-S | Y | Y | N |  | Sized members; penetrations coordinated
S-201 | Structure |  | ZZ | General arrangement drawings (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | Structural lead | TIDP-S | N | Y | N
M-200 | Mechanical |  | ZZ | Mechanical model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | MEP lead | TIDP-M | Y | Y | N |  | Real equipment; risers fixed
M-201 | Mechanical |  | ZZ | HVAC layouts (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | MEP lead | TIDP-M | N | Y | N
E-200 | Electrical |  | ZZ | Electrical model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | MEP lead | TIDP-E | Y | Y | N |  | Power, lighting and containment routed; boards placed
E-201 | Electrical |  | ZZ | Power and lighting layouts (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | MEP lead | TIDP-E | N | Y | N |  | Lighting layouts under role E (G-03)
P-200 | Public Health |  | ZZ | Plumbing and drainage model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | MEP lead | TIDP-P | Y | Y | N |  | Real pipework with code falls; fixtures placed
P-201 | Public Health |  | ZZ | Plumbing and drainage layouts (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | MEP lead | TIDP-P | N | Y | N
FP-200 | Fire Protection |  | ZZ | Fire strategy and suppression layout | Model/Document | M3 | 2.2 Deliverable B | 300 | RVT/PDF | S2 | Shared | 2 | 4 |  |  |  | Fire lead | TIDP-FP | Y | Y | N |  | Sprinkler and detection layout
LV-200 | Low Voltage |  | ZZ | Low voltage containment and equipment rooms | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | LV lead | TIDP-LV | Y | Y | N
G-200 | Civil and Site |  | 00 | Site model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | Civil lead | TIDP-G | Y | Y | N |  | Real site model; drainage and access
G-201 | Civil and Site |  | 00 | Site and drainage drawings (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | Civil lead | TIDP-G | N | Y | N
Z-210 | Information Management |  | ZZ | Coordination reports (fortnightly) and Deliverable B clash close-out | Report | CR | 2.2 Deliverable B | 300 | PDF/BCF | S2 | Shared | 2 | 4 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | No unresolved high-priority clashes at the gate
Z-211 | Information Management |  | ZZ | Federated model | Model | M3 | 2.2 Deliverable B | 300 | NWC/NWD/IFC | S2 | Shared | 4 | 4 |  |  |  | Information Manager | TIDP-Z | Y | Y | N |  | Milestone NWD archived
Z-212 | QS / Cost |  | ZZ | Bill of quantities (preliminary) | Schedule | BQ | 2.2 Deliverable B | 300 | XLSX | S2 | Shared | 4 | 4 |  |  |  | Quantity Surveyor | TIDP-Q | Y | N | Y |  | Derived from the coordinated models by the QS
FF-200 | FF&E |  | ZZ | FF&E and finishes register (first Fohlio exchange) | Schedule | SC | 2.2 Deliverable B | 300 | CSV/XLSX | S2 | Shared | 4 | 4 |  |  |  | Interior Designer | TIDP-FF | N | N | Y |  | Matched on room number
Z-213 | Information Management |  | ZZ | Deliverable B gate pack, LOD 300 verification and compliance report | Document | RP | 2.2 Deliverable B | 300 | PDF | S4 | Shared | 4 | 4 |  |  |  | Information Manager | TIDP-Z | Y | N | N
Z-214 | Information Management |  | ZZ | Deliverable B Owner review set and comment close-out report | Document | RP | 2.2 Deliverable B | 300 | PDF | S3 | Shared | 4 | 5 |  |  |  | Information Manager | TIDP-Z | Y | N | N
A-300 | Architecture |  | ZZ | Architectural model | Model | M3 | 2.3 Deliverable C | 350 | RVT/IFC | S4 | Shared | 5 | 8 |  |  |  | Architecture lead | TIDP-A | Y | Y | N |  | Interfaces resolved
A-301 | Architecture |  | ZZ | Full drawing set (100%) and details | Drawing | SH | 2.3 Deliverable C | 350 | PDF/DWG | S4 | Shared | 8 | 8 |  |  |  | Architecture lead | TIDP-A | Y | Y | N
A-302 | Architecture |  | ZZ | Room data sheets (complete) | Room data sheet | RD | 2.3 Deliverable C | 350 | PDF | S4 | Shared | 8 | 8 |  |  |  | Architecture lead | TIDP-A | N | N | N |  | Generated from the reconciled Fohlio data
S-300 | Structure |  | ZZ | Structural model | Model | M3 | 2.3 Deliverable C | 350 | RVT/IFC | S4 | Shared | 5 | 8 |  |  |  | Structural lead | TIDP-S | Y | Y | N |  | Connections resolved
S-301 | Structure |  | ZZ | Structural drawing set (100%) | Drawing | SH | 2.3 Deliverable C | 350 | PDF/DWG | S4 | Shared | 8 | 8 |  |  |  | Structural lead | TIDP-S | Y | Y | N
M-300 | Mechanical |  | ZZ | Mechanical model | Model | M3 | 2.3 Deliverable C | 350 | RVT/IFC | S4 | Shared | 5 | 8 |  |  |  | MEP lead | TIDP-M | Y | Y | N |  | Systems complete and connected; equipment data
M-301 | Mechanical |  | ZZ | HVAC drawing set (100%) | Drawing | SH | 2.3 Deliverable C | 350 | PDF/DWG | S4 | Shared | 8 | 8 |  |  |  | MEP lead | TIDP-M | Y | Y | N
M-302 | Mechanical |  | ZZ | HVAC load and sizing schedules | Schedule | SC | 2.3 Deliverable C | 350 | PDF/XLSX | S4 | Shared | 8 | 8 |  |  |  | MEP lead | TIDP-M | Y | N | N
M-303 | Mechanical |  | ZZ | BMS point-naming convention and point data on serviceable elements | Schedule | SC | 2.3 Deliverable C | 350 | XLSX | S3 | Shared | 8 | 8 |  |  |  | MEP lead | TIDP-M | N | N | N |  | Agreed with the controls contractor
E-300 | Electrical |  | ZZ | Electrical model and drawing set (100%) | Model/Drawing | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | MEP lead | TIDP-E | Y | Y | N
E-301 | Electrical |  | ZZ | Panel schedules and single-line diagrams | Schedule/Drawing | SH | 2.3 Deliverable C | 350 | PDF/XLSX | S4 | Shared | 8 | 8 |  |  |  | MEP lead | TIDP-E | Y | Y | N |  | Sheets in the 6xxx and 7xxx bands
P-300 | Public Health |  | ZZ | Plumbing model and drawing set (100%) | Model/Drawing | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | MEP lead | TIDP-P | Y | Y | N
FP-300 | Fire Protection |  | ZZ | Fire strategy and model (100%) | Model/Document | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | Fire lead | TIDP-FP | Y | Y | N |  | Transition to the design-build contractor agreed
LV-300 | Low Voltage |  | ZZ | Communications and security model and drawings | Model/Drawing | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | LV lead | TIDP-LV | Y | Y | N |  | Restricted-information handling per BEP 8.1
G-300 | Civil and Site |  | 00 | Civil and site model and drawings (100%) | Model/Drawing | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | Civil lead | TIDP-G | Y | Y | N
Z-310 | QS / Cost |  | ZZ | Bill of quantities (tender) | Schedule | BQ | 2.3 Deliverable C | 350 | XLSX | S4 | Shared | 8 | 8 |  |  |  | Quantity Surveyor | TIDP-Q | Y | N | Y
Z-311 | All disciplines |  | ZZ | Specifications (RIB SpecLink, CSI MasterFormat) | Specification | SP | 2.3 Deliverable C | 350 | PDF | S4 | Shared | 8 | 8 |  |  |  | Task Team Managers | TIDP-ALL | Y | N | Y |  | Issued sets archived with the milestone
Z-312 | Information Management |  | ZZ | Specification reconciliation report (model vs SpecLink) | Report | RP | 2.3 Deliverable C | 350 | XLSX/PDF | S4 | Shared | 8 | 8 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Gaps closed or formally accepted
FF-300 | FF&E |  | ZZ | FF&E specifications and schedule | Schedule | SC | 2.3 Deliverable C | 350 | XLSX/PDF | S4 | Shared | 8 | 8 |  |  |  | Interior Designer | TIDP-FF | Y | N | Y |  | Reconciled to Fohlio
Z-313 | Information Management |  | ZZ | Deliverable C gate pack, LOD 350 verification and compliance report | Document | RP | 2.3 Deliverable C | 350 | PDF | S4 | Shared | 8 | 8 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Includes FF&E currency report
Z-314 | Information Management |  | ZZ | Deliverable C Owner review set and comment close-out report | Document | RP | 2.3 Deliverable C | 350 | PDF | S3 | Shared | 8 | 9 |  |  |  | Information Manager | TIDP-Z | Y | N | N
Z-400 | Information Management |  | ZZ | Tender documents | Document | RP | 2.4 Tender | n/a | PDF | A1 | Published | 9 | 9 |  |  |  | Lead Appointed Party | TIDP-Z | N | N | N |  | Issued from the CDE at A1
Z-401 | Information Management |  | ZZ | Tender query and addendum log | Report | RP | 2.4 Tender | n/a | XLSX | S2 | Shared | 9 | 11 |  |  |  | Lead Appointed Party | TIDP-Z | N | N | N |  | Queries answered as formal RFIs
Z-410 | Information Management |  | ZZ | Conformed set | Drawing | SH | 2.5 Conformed set | 350 | PDF/DWG | A1 | Published | 11 | 11 |  |  |  | Lead Appointed Party | TIDP-Z | Y | Y | N |  | Addenda incorporated; superseded revisions archived
Z-411 | Information Management |  | ZZ | Conformed-set conformance audit and compliance report | Report | RP | 2.5 Conformed set | 350 | PDF | S4 | Shared | 11 | 11 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Milestone NWD archive
A-500 | Architecture |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | Architecture lead | TIDP-A | Y | Y | N
S-500 | Structure |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | Structural lead | TIDP-S | Y | Y | N
M-500 | Mechanical |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | MEP lead | TIDP-M | Y | Y | N |  | Maintenance type on plumbing fixtures from LOD 400
E-500 | Electrical |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | MEP lead | TIDP-E | Y | Y | N
P-500 | Public Health |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | MEP lead | TIDP-P | Y | Y | N
FP-500 | Fire Protection |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | Design-build fire contractor | TIDP-FP | Y | Y | N |  | D-B contractor becomes engineer of record
LV-500 | Low Voltage |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | LV lead | TIDP-LV | Y | Y | N
G-500 | Civil and Site |  | 00 | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | Civil lead | TIDP-G | Y | Y | N
C-500 | Contractor |  | ZZ | Shop drawings and fabrication models (steel, MEP modules, façade) | Model/Drawing | M3 | 3.1 Construction | 400 | RVT/IFC/PDF | S2 | Shared | 12 | 43 |  |  |  | Contractor | TIDP-C | Y | Y | N |  | Linked into the federation
Z-510 | Information Management |  | ZZ | Request for information and submittal register | Report | RP | 3.1 Construction | 400 | XLSX | S2 | Shared | 12 | 43 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Maintained continuously
Z-511 | Information Management |  | ZZ | Monthly BIM status report (construction) | Report | RP | 3.1 Construction | 400 | PDF | S2 | Shared | 12 | 49 |  |  |  | Information Manager | TIDP-Z | N | N | N
Z-512 | Contractor |  | ZZ | As-built capture (progressive) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | S2 | Shared | 12 | 43 |  |  |  | Contractor | TIDP-C | Y | Y | N |  | Clouded changes in official documentation; current to within one month
Z-513 | Contractor |  | ZZ | Asset data capture (tiered schedule, BEP 14) | Schedule | SC | 3.1 Construction | 400 | XLSX | S2 | Shared | 12 | 47 |  |  |  | Contractor | TIDP-C | Y | Y | Y |  | Tier A serialised plant, B maintainable devices, C warranted fabric
Z-514 | Information Management |  | ZZ | Asset data completeness report (monthly, by tier and volume) | Report | RP | 3.1 Construction | 400 | XLSX/PDF | S2 | Shared | 12 | 47 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | A tier below 95% at Gate D is a gate failure
Z-515 | Information Management |  | ZZ | Quarterly model-health audit | Report | RP | 3.1 Construction | 400 | PDF | S2 | Shared | 12 | 43 |  |  |  | Information Manager | TIDP-Z | N | N | N
Z-516 | Information Management |  | ZZ | Revision register | Schedule | SC | 3.1 Construction | 400 | XLSX | S2 | Shared | 12 | 43 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Clouds and revision schedules
Z-517 | Information Management |  | ZZ | Contractor and specialist induction record | Document | RP | 3.1 Construction | n/a | PDF | S2 | Shared | 12 | 12 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Including the design-build fire and controls contractors
Z-518 | Information Management |  | ZZ | Construction-stage coordination reports (monthly) | Report | CR | 3.1 Construction | 400 | PDF/BCF | S2 | Shared | 12 | 43 |  |  |  | Information Manager | TIDP-Z | N | N | N
M-520 | Mechanical |  | ZZ | Commissioning point list (Niagara) | Schedule | SC | 3.1 Construction | 400 | CSV | S2 | Shared | 40 | 40 |  |  |  | MEP lead | TIDP-M | Y | N | Y |  | Produced from the model for the controls contractor
FF-600 | FF&E |  | ZZ | FF&E final schedule and procurement record | Schedule | SC | 3.2 FF&E | 400 | XLSX | A1 | Published | 44 | 47 |  |  |  | Interior Designer | TIDP-FF | Y | N | Y |  | Reconciled item by item
FF-601 | FF&E |  | ZZ | Installed FF&E and finishes reconciliation report (model vs Fohlio) | Report | RP | 3.2 FF&E | 400 | XLSX/PDF | S2 | Shared | 47 | 47 |  |  |  | Information Manager | TIDP-FF | Y | N | Y |  | No unlinked items; O&M data collected in Fohlio
A-700 | Architecture |  | ZZ | As-built architectural model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | Architecture lead | TIDP-A | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager
S-700 | Structure |  | ZZ | As-built structural model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | Structural lead | TIDP-S | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager
M-700 | Mechanical |  | ZZ | As-built mechanical model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | MEP lead | TIDP-M | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager
E-700 | Electrical |  | ZZ | As-built electrical model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | MEP lead | TIDP-E | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager
P-700 | Public Health |  | ZZ | As-built plumbing and drainage model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | MEP lead | TIDP-P | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager
FP-700 | Fire Protection |  | ZZ | As-built fire protection model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | Design-build fire contractor | TIDP-FP | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager
LV-700 | Low Voltage |  | ZZ | As-built low voltage model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | LV lead | TIDP-LV | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager
G-700 | Civil and Site |  | 00 | As-built civil and site model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | Civil lead | TIDP-G | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager
C-700 | Contractor |  | ZZ | Final as-built documentation, commissioning records, warranties and O&M documents | Document | RP | 3.3 Deliverable D | 500 | PDF | A1 | Published | 48 | 48 |  |  |  | Contractor | TIDP-C | Y | Y | Y |  | Input to the record model verification
Z-700 | Information Management |  | ZZ | COBie 2.4 handover dataset — CONDITIONAL on Owner instruction | Schedule | SC | 3.3 Deliverable D | 500 | XLSX | A1 | Published | 48 | 49 |  |  |  | Information Manager | TIDP-Z | N | N | Y |  | Produced only if instructed as an additional service
Z-701 | Information Management |  | ZZ | Operation and maintenance / asset data pack (Fohlio) | Document | RP | 3.3 Deliverable D | 500 | PDF | A1 | Published | 48 | 49 |  |  |  | Information Manager | TIDP-Z | Y | N | Y |  | O&M manuals published through Fohlio by the Interior Designer (A1)
Z-702 | Information Management |  | ZZ | Reconciled building management system point register (digital-twin baseline) | Schedule | SC | 3.3 Deliverable D | 500 | CSV/PDF | A1 | Published | 49 | 49 |  |  |  | Information Manager | TIDP-Z | Y | N | Y |  | Model reconciled to the live Niagara station
Z-703 | Information Management |  | ZZ | Deliverable D gate pack: LOD 500 verification and asset data completeness | Document | RP | 3.3 Deliverable D | 500 | PDF | A1 | Published | 49 | 49 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Days 10 to 35 of the close-out plan
Z-704 | Information Management |  | ZZ | Final transmittal and project archive | Document | TR | 3.3 Deliverable D | 500 | PDF | A1 | Archived | 49 | 49 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Days 50 to 60
Z-705 | All disciplines |  | ZZ | Native design, calculation, energy and system program files (A1 Deliverable D) | Document | RP | 3.3 Deliverable D | 500 | Native | A1 | Published | 48 | 49 |  |  |  | Task Team Managers | TIDP-ALL | Y | N | Y
Z-706 | Information Management |  | ZZ | Final drawing register | Schedule | SC | 3.3 Deliverable D | 500 | XLSX/PDF | A1 | Published | 49 | 49 |  |  |  | Information Manager | TIDP-Z | N | N | N

## TIDP-Z
Task Information Delivery Plan — Information Management
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-Z
Scope | Information Management
Appointed party | Symbion Consulting Group Studios — Information Manager
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
Z-000 | Information Management |  | ZZ | BIM Execution Plan | Document | RP | Mobilisation | n/a | DOCX/PDF | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Baselined at mobilisation; reissued per stage
Z-001 | Information Management |  | ZZ | Master Information Delivery Plan | Schedule | SC | Mobilisation | n/a | XLSX | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Aggregated from all TIDPs; monthly and per drop
Z-002 | Information Management |  | ZZ | Project Delivery Playbook | Document | RP | Mobilisation | n/a | DOCX/PDF | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Reference RP-Z-0002
Z-003 | Information Management |  | ZZ | Responsibility matrix (RACI) | Schedule | SC | Mobilisation | n/a | XLSX | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Reference SC-Z-0002
Z-004 | Information Management |  | ZZ | Project template, family library and title blocks | Model | M3 | Mobilisation | n/a | RVT/RFA | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Coordinates, levels, grids, worksets, shared parameters bound
Z-005 | Information Management |  | ZZ | Originator code register | Schedule | SC | Mobilisation | n/a | XLSX | A1 | Published | 0 | 0 |  |  |  | Lead Appointed Party | TIDP-Z | Y | N | N |  | Required before any container is numbered; 3-character codes
Z-007 | Information Management |  | ZZ | Standards reconciliation schedule (BEP 4.1.3) | Schedule | SC | Mobilisation | n/a | XLSX/PDF | S3 | Shared | 0 | 8 |  |  |  | All disciplines | TIDP-Z | Y | N | N |  | Opened at mobilisation; closed before Stage 2.3
Z-008 | Information Management |  | ZZ | Shared coordinates seed model | Model | M3 | Mobilisation | n/a | RVT | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Survey point, project base point, true north, levels and grids
Z-009 | Information Management |  | ZZ | Level and grid register | Schedule | SC | Mobilisation | n/a | XLSX/PDF | A1 | Published | 0 | 0 |  |  |  | Lead Appointed Party | TIDP-Z | Y | N | N |  | Reference SC-Z-0003
Z-011 | Information Management |  | ZZ | Software and version register | Schedule | SC | Mobilisation | n/a | XLSX | A1 | Published | 0 | 0 |  |  |  | All parties | TIDP-Z | N | N | N |  | Revit 2025 locked project-wide
Z-012 | Information Management |  | ZZ | CDE folder structure and permission matrix | Document | RP | Mobilisation | n/a | PDF | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | ACC provisioned; seats confirmed for every party (E-01)
Z-013 | Information Management |  | ZZ | Information classification and access schedule | Document | RP | Mobilisation | n/a | PDF | A1 | Published | 0 | 0 |  |  |  | Appointing Party | TIDP-Z | Y | N | N |  | Restricted spaces and systems classified before modelling begins
Z-014 | Information Management |  | ZZ | Clash matrix and tolerance schedule | Document | RP | Mobilisation | n/a | PDF | S3 | Shared | 1 | 1 |  |  |  | MEP and structural leads | TIDP-Z | Y | N | N |  | Required before the first coordination cycle of Stage 2.2
Z-015 | Information Management |  | ZZ | IFC export configuration | Document | RP | Mobilisation | n/a | PDF/JSON | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Issued centrally
Z-016 | Information Management |  | ZZ | Shared parameter file | Document | RP | Mobilisation | n/a | TXT | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Central ownership
Z-017 | Information Management |  | ZZ | Capability and capacity assessment | Report | RP | Mobilisation | n/a | XLSX | S3 | Shared | 1 | 1 |  |  |  | Lead Appointed Party | TIDP-Z | N | N | N |  | ISO 19650-2; the Stage 0 test model is its practical form
Z-018 | Information Management |  | ZZ | Standards localisation note (Owner standards to Ugandan practice) | Document | RP | Mobilisation | n/a | DOCX/PDF | S3 | Shared | 0 | 1 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Reference RP-Z-0005; weeks 2–3 after the Owner standards are received
Z-019 | Information Management |  | ZZ | Stage 0 gate record (test model shared by every appointed party) | Report | RP | Mobilisation | n/a | PDF | S3 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | No discipline enters the fortnightly cycle before this
Z-020 | Information Management |  | ZZ | Monthly BIM status report (design stage) | Report | RP | Mobilisation | n/a | PDF | S2 | Shared | 1 | 11 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | KPIs per BEP 10.5
Z-021 | Information Management |  | ZZ | Kickoff induction record and BEP acknowledgement | Document | RP | Mobilisation | n/a | PDF | A1 | Published | 0 | 1 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Attendance and signed acknowledgement from every task team
Z-022 | Information Management |  | ZZ | Document Control Standard (reissued to P02 codes) | Document | RP | Mobilisation | n/a | DOCX/PDF | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | KUT-SMB-ZZ-ZZ-RP-Z-0003. Container naming, sheet number bands, revision, authorisation, transmittal, superseded/cancelled/replaced notices, number retirement
Z-024 | Information Management |  | ZZ | Drawing register, transmittal and notice templates | Document | TR | Mobilisation | n/a | XLSX/DOCX | A1 | Published | 0 | 0 |  |  |  | Information Manager | TIDP-Z | N | N | N
Z-010 | Information Management |  | ZZ | Federated coordination model | Model | M3 | 2.1 Deliverable A | 200 | NWC/NWD/IFC | S1 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | Y | Y | N |  | First federation; container M3-Z-0001
Z-110 | Information Management |  | ZZ | Basis of design report | Document | RP | 2.1 Deliverable A | 200 | DOCX/PDF | S3 | Shared | 1 | 1 |  |  |  | Lead Appointed Party | TIDP-Z | N | N | N |  | Design intent
Z-111 | Information Management |  | ZZ | Area schedule reconciled to the brief | Schedule | SC | 2.1 Deliverable A | 200 | XLSX/PDF | S3 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Gate condition
Z-112 | Information Management |  | ZZ | Deliverable A gate pack and compliance report | Document | RP | 2.1 Deliverable A | 200 | PDF | S4 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Contents per Playbook Appendix B
Z-113 | Information Management |  | ZZ | Deliverable A Owner review set and comment close-out report | Document | RP | 2.1 Deliverable A | 200 | PDF | S3 | Shared | 1 | 2 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Comments closed before the gate
Z-114 | Information Management |  | ZZ | Baseline model-health report | Report | RP | 2.1 Deliverable A | 200 | PDF | S2 | Shared | 1 | 1 |  |  |  | Information Manager | TIDP-Z | N | N | N
Z-210 | Information Management |  | ZZ | Coordination reports (fortnightly) and Deliverable B clash close-out | Report | CR | 2.2 Deliverable B | 300 | PDF/BCF | S2 | Shared | 2 | 4 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | No unresolved high-priority clashes at the gate
Z-211 | Information Management |  | ZZ | Federated model | Model | M3 | 2.2 Deliverable B | 300 | NWC/NWD/IFC | S2 | Shared | 4 | 4 |  |  |  | Information Manager | TIDP-Z | Y | Y | N |  | Milestone NWD archived
Z-213 | Information Management |  | ZZ | Deliverable B gate pack, LOD 300 verification and compliance report | Document | RP | 2.2 Deliverable B | 300 | PDF | S4 | Shared | 4 | 4 |  |  |  | Information Manager | TIDP-Z | Y | N | N
Z-214 | Information Management |  | ZZ | Deliverable B Owner review set and comment close-out report | Document | RP | 2.2 Deliverable B | 300 | PDF | S3 | Shared | 4 | 5 |  |  |  | Information Manager | TIDP-Z | Y | N | N
Z-312 | Information Management |  | ZZ | Specification reconciliation report (model vs SpecLink) | Report | RP | 2.3 Deliverable C | 350 | XLSX/PDF | S4 | Shared | 8 | 8 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Gaps closed or formally accepted
Z-313 | Information Management |  | ZZ | Deliverable C gate pack, LOD 350 verification and compliance report | Document | RP | 2.3 Deliverable C | 350 | PDF | S4 | Shared | 8 | 8 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Includes FF&E currency report
Z-314 | Information Management |  | ZZ | Deliverable C Owner review set and comment close-out report | Document | RP | 2.3 Deliverable C | 350 | PDF | S3 | Shared | 8 | 9 |  |  |  | Information Manager | TIDP-Z | Y | N | N
Z-400 | Information Management |  | ZZ | Tender documents | Document | RP | 2.4 Tender | n/a | PDF | A1 | Published | 9 | 9 |  |  |  | Lead Appointed Party | TIDP-Z | N | N | N |  | Issued from the CDE at A1
Z-401 | Information Management |  | ZZ | Tender query and addendum log | Report | RP | 2.4 Tender | n/a | XLSX | S2 | Shared | 9 | 11 |  |  |  | Lead Appointed Party | TIDP-Z | N | N | N |  | Queries answered as formal RFIs
Z-410 | Information Management |  | ZZ | Conformed set | Drawing | SH | 2.5 Conformed set | 350 | PDF/DWG | A1 | Published | 11 | 11 |  |  |  | Lead Appointed Party | TIDP-Z | Y | Y | N |  | Addenda incorporated; superseded revisions archived
Z-411 | Information Management |  | ZZ | Conformed-set conformance audit and compliance report | Report | RP | 2.5 Conformed set | 350 | PDF | S4 | Shared | 11 | 11 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Milestone NWD archive
Z-510 | Information Management |  | ZZ | Request for information and submittal register | Report | RP | 3.1 Construction | 400 | XLSX | S2 | Shared | 12 | 43 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Maintained continuously
Z-511 | Information Management |  | ZZ | Monthly BIM status report (construction) | Report | RP | 3.1 Construction | 400 | PDF | S2 | Shared | 12 | 49 |  |  |  | Information Manager | TIDP-Z | N | N | N
Z-514 | Information Management |  | ZZ | Asset data completeness report (monthly, by tier and volume) | Report | RP | 3.1 Construction | 400 | XLSX/PDF | S2 | Shared | 12 | 47 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | A tier below 95% at Gate D is a gate failure
Z-515 | Information Management |  | ZZ | Quarterly model-health audit | Report | RP | 3.1 Construction | 400 | PDF | S2 | Shared | 12 | 43 |  |  |  | Information Manager | TIDP-Z | N | N | N
Z-516 | Information Management |  | ZZ | Revision register | Schedule | SC | 3.1 Construction | 400 | XLSX | S2 | Shared | 12 | 43 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Clouds and revision schedules
Z-517 | Information Management |  | ZZ | Contractor and specialist induction record | Document | RP | 3.1 Construction | n/a | PDF | S2 | Shared | 12 | 12 |  |  |  | Information Manager | TIDP-Z | N | N | N |  | Including the design-build fire and controls contractors
Z-518 | Information Management |  | ZZ | Construction-stage coordination reports (monthly) | Report | CR | 3.1 Construction | 400 | PDF/BCF | S2 | Shared | 12 | 43 |  |  |  | Information Manager | TIDP-Z | N | N | N
Z-700 | Information Management |  | ZZ | COBie 2.4 handover dataset — CONDITIONAL on Owner instruction | Schedule | SC | 3.3 Deliverable D | 500 | XLSX | A1 | Published | 48 | 49 |  |  |  | Information Manager | TIDP-Z | N | N | Y |  | Produced only if instructed as an additional service
Z-701 | Information Management |  | ZZ | Operation and maintenance / asset data pack (Fohlio) | Document | RP | 3.3 Deliverable D | 500 | PDF | A1 | Published | 48 | 49 |  |  |  | Information Manager | TIDP-Z | Y | N | Y |  | O&M manuals published through Fohlio by the Interior Designer (A1)
Z-702 | Information Management |  | ZZ | Reconciled building management system point register (digital-twin baseline) | Schedule | SC | 3.3 Deliverable D | 500 | CSV/PDF | A1 | Published | 49 | 49 |  |  |  | Information Manager | TIDP-Z | Y | N | Y |  | Model reconciled to the live Niagara station
Z-703 | Information Management |  | ZZ | Deliverable D gate pack: LOD 500 verification and asset data completeness | Document | RP | 3.3 Deliverable D | 500 | PDF | A1 | Published | 49 | 49 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Days 10 to 35 of the close-out plan
Z-704 | Information Management |  | ZZ | Final transmittal and project archive | Document | TR | 3.3 Deliverable D | 500 | PDF | A1 | Archived | 49 | 49 |  |  |  | Information Manager | TIDP-Z | Y | N | N |  | Days 50 to 60
Z-706 | Information Management |  | ZZ | Final drawing register | Schedule | SC | 3.3 Deliverable D | 500 | XLSX/PDF | A1 | Published | 49 | 49 |  |  |  | Information Manager | TIDP-Z | N | N | N

## TIDP-A
Task Information Delivery Plan — Architecture and interiors
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-A
Scope | Architecture and interiors
Appointed party | [FILL — architecture practice]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
A-100 | Architecture |  | ZZ | Architectural model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | Architecture lead | TIDP-A | Y | Y | N |  | Massing and generic systems; rooms placed
A-101 | Architecture |  | ZZ | Deliverable A drawing set | Drawing | SH | 2.1 Deliverable A | 200 | PDF/DWG | S3 | Shared | 1 | 1 |  |  |  | Architecture lead | TIDP-A | N | N | N
A-200 | Architecture |  | ZZ | Architectural model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | Architecture lead | TIDP-A | Y | Y | N |  | Real geometry, correctly located; no placeholder families
A-201 | Architecture |  | ZZ | General arrangement plans, sections and elevations (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | Architecture lead | TIDP-A | N | Y | N
A-202 | Architecture |  | ZZ | Door and window schedules | Schedule | SC | 2.2 Deliverable B | 300 | PDF/XLSX | S2 | Shared | 4 | 4 |  |  |  | Architecture lead | TIDP-A | N | N | N
A-203 | Architecture |  | ZZ | Room data sheets (key spaces) | Room data sheet | RD | 2.2 Deliverable B | 300 | PDF | S2 | Shared | 4 | 4 |  |  |  | Architecture lead | TIDP-A | N | N | N |  | Complete set at Deliverable C (A-302)
A-204 | Architecture |  | ZZ | Existing conditions and removals plan | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | Architecture lead | TIDP-A | N | N | N |  | Demolition classification is a manual task; BEP 10.4
A-300 | Architecture |  | ZZ | Architectural model | Model | M3 | 2.3 Deliverable C | 350 | RVT/IFC | S4 | Shared | 5 | 8 |  |  |  | Architecture lead | TIDP-A | Y | Y | N |  | Interfaces resolved
A-301 | Architecture |  | ZZ | Full drawing set (100%) and details | Drawing | SH | 2.3 Deliverable C | 350 | PDF/DWG | S4 | Shared | 8 | 8 |  |  |  | Architecture lead | TIDP-A | Y | Y | N
A-302 | Architecture |  | ZZ | Room data sheets (complete) | Room data sheet | RD | 2.3 Deliverable C | 350 | PDF | S4 | Shared | 8 | 8 |  |  |  | Architecture lead | TIDP-A | N | N | N |  | Generated from the reconciled Fohlio data
A-500 | Architecture |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | Architecture lead | TIDP-A | Y | Y | N
A-700 | Architecture |  | ZZ | As-built architectural model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | Architecture lead | TIDP-A | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager

## TIDP-S
Task Information Delivery Plan — Structural
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-S
Scope | Structural
Appointed party | [FILL — structural engineer]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
S-100 | Structure |  | ZZ | Structural model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | Structural lead | TIDP-S | Y | Y | N |  | Indicative frame and foundations
S-200 | Structure |  | ZZ | Structural model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | Structural lead | TIDP-S | Y | Y | N |  | Sized members; penetrations coordinated
S-201 | Structure |  | ZZ | General arrangement drawings (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | Structural lead | TIDP-S | N | Y | N
S-300 | Structure |  | ZZ | Structural model | Model | M3 | 2.3 Deliverable C | 350 | RVT/IFC | S4 | Shared | 5 | 8 |  |  |  | Structural lead | TIDP-S | Y | Y | N |  | Connections resolved
S-301 | Structure |  | ZZ | Structural drawing set (100%) | Drawing | SH | 2.3 Deliverable C | 350 | PDF/DWG | S4 | Shared | 8 | 8 |  |  |  | Structural lead | TIDP-S | Y | Y | N
S-500 | Structure |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | Structural lead | TIDP-S | Y | Y | N
S-700 | Structure |  | ZZ | As-built structural model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | Structural lead | TIDP-S | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager

## TIDP-M
Task Information Delivery Plan — Mechanical
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-M
Scope | Mechanical
Appointed party | [FILL — MEP engineer]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
M-100 | Mechanical |  | ZZ | Mechanical model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | MEP lead | TIDP-M | Y | Y | N |  | Plant space allocation, primary routes
M-200 | Mechanical |  | ZZ | Mechanical model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | MEP lead | TIDP-M | Y | Y | N |  | Real equipment; risers fixed
M-201 | Mechanical |  | ZZ | HVAC layouts (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | MEP lead | TIDP-M | N | Y | N
M-300 | Mechanical |  | ZZ | Mechanical model | Model | M3 | 2.3 Deliverable C | 350 | RVT/IFC | S4 | Shared | 5 | 8 |  |  |  | MEP lead | TIDP-M | Y | Y | N |  | Systems complete and connected; equipment data
M-301 | Mechanical |  | ZZ | HVAC drawing set (100%) | Drawing | SH | 2.3 Deliverable C | 350 | PDF/DWG | S4 | Shared | 8 | 8 |  |  |  | MEP lead | TIDP-M | Y | Y | N
M-302 | Mechanical |  | ZZ | HVAC load and sizing schedules | Schedule | SC | 2.3 Deliverable C | 350 | PDF/XLSX | S4 | Shared | 8 | 8 |  |  |  | MEP lead | TIDP-M | Y | N | N
M-303 | Mechanical |  | ZZ | BMS point-naming convention and point data on serviceable elements | Schedule | SC | 2.3 Deliverable C | 350 | XLSX | S3 | Shared | 8 | 8 |  |  |  | MEP lead | TIDP-M | N | N | N |  | Agreed with the controls contractor
M-500 | Mechanical |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | MEP lead | TIDP-M | Y | Y | N |  | Maintenance type on plumbing fixtures from LOD 400
M-520 | Mechanical |  | ZZ | Commissioning point list (Niagara) | Schedule | SC | 3.1 Construction | 400 | CSV | S2 | Shared | 40 | 40 |  |  |  | MEP lead | TIDP-M | Y | N | Y |  | Produced from the model for the controls contractor
M-700 | Mechanical |  | ZZ | As-built mechanical model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | MEP lead | TIDP-M | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager

## TIDP-E
Task Information Delivery Plan — Electrical
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-E
Scope | Electrical
Appointed party | [FILL — MEP engineer]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
E-100 | Electrical |  | ZZ | Electrical model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | MEP lead | TIDP-E | Y | Y | N |  | Generic equipment and main containment
E-200 | Electrical |  | ZZ | Electrical model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | MEP lead | TIDP-E | Y | Y | N |  | Power, lighting and containment routed; boards placed
E-201 | Electrical |  | ZZ | Power and lighting layouts (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | MEP lead | TIDP-E | N | Y | N |  | Lighting layouts under role E (G-03)
E-300 | Electrical |  | ZZ | Electrical model and drawing set (100%) | Model/Drawing | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | MEP lead | TIDP-E | Y | Y | N
E-301 | Electrical |  | ZZ | Panel schedules and single-line diagrams | Schedule/Drawing | SH | 2.3 Deliverable C | 350 | PDF/XLSX | S4 | Shared | 8 | 8 |  |  |  | MEP lead | TIDP-E | Y | Y | N |  | Sheets in the 6xxx and 7xxx bands
E-500 | Electrical |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | MEP lead | TIDP-E | Y | Y | N
E-700 | Electrical |  | ZZ | As-built electrical model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | MEP lead | TIDP-E | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager

## TIDP-P
Task Information Delivery Plan — Public health (plumbing and drainage)
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-P
Scope | Public health (plumbing and drainage)
Appointed party | [FILL — MEP engineer]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
P-100 | Public Health |  | ZZ | Plumbing and drainage model | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | MEP lead | TIDP-P | Y | Y | N |  | Primary routes; font systems indicated
P-200 | Public Health |  | ZZ | Plumbing and drainage model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | MEP lead | TIDP-P | Y | Y | N |  | Real pipework with code falls; fixtures placed
P-201 | Public Health |  | ZZ | Plumbing and drainage layouts (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | MEP lead | TIDP-P | N | Y | N
P-300 | Public Health |  | ZZ | Plumbing model and drawing set (100%) | Model/Drawing | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | MEP lead | TIDP-P | Y | Y | N
P-500 | Public Health |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | MEP lead | TIDP-P | Y | Y | N
P-700 | Public Health |  | ZZ | As-built plumbing and drainage model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | MEP lead | TIDP-P | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager

## TIDP-FP
Task Information Delivery Plan — Fire protection
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-FP
Scope | Fire protection
Appointed party | [FILL — fire engineer / design-build contractor]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
FP-200 | Fire Protection |  | ZZ | Fire strategy and suppression layout | Model/Document | M3 | 2.2 Deliverable B | 300 | RVT/PDF | S2 | Shared | 2 | 4 |  |  |  | Fire lead | TIDP-FP | Y | Y | N |  | Sprinkler and detection layout
FP-300 | Fire Protection |  | ZZ | Fire strategy and model (100%) | Model/Document | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | Fire lead | TIDP-FP | Y | Y | N |  | Transition to the design-build contractor agreed
FP-500 | Fire Protection |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | Design-build fire contractor | TIDP-FP | Y | Y | N |  | D-B contractor becomes engineer of record
FP-700 | Fire Protection |  | ZZ | As-built fire protection model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | Design-build fire contractor | TIDP-FP | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager

## TIDP-LV
Task Information Delivery Plan — Low voltage and communications
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-LV
Scope | Low voltage and communications
Appointed party | [FILL — LV engineer]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
LV-200 | Low Voltage |  | ZZ | Low voltage containment and equipment rooms | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | LV lead | TIDP-LV | Y | Y | N
LV-300 | Low Voltage |  | ZZ | Communications and security model and drawings | Model/Drawing | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | LV lead | TIDP-LV | Y | Y | N |  | Restricted-information handling per BEP 8.1
LV-500 | Low Voltage |  | ZZ | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | LV lead | TIDP-LV | Y | Y | N
LV-700 | Low Voltage |  | ZZ | As-built low voltage model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | LV lead | TIDP-LV | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager

## TIDP-G
Task Information Delivery Plan — Civil and site
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-G
Scope | Civil and site
Appointed party | [FILL — civil engineer]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
G-100 | Civil and Site |  | 00 | Site model and levels | Model | M3 | 2.1 Deliverable A | 200 | RVT/IFC | S2 | Shared | 1 | 1 |  |  |  | Civil lead | TIDP-G | Y | Y | N |  | Site levels, access, drainage strategy; scope to confirm
G-200 | Civil and Site |  | 00 | Site model | Model | M3 | 2.2 Deliverable B | 300 | RVT/IFC | S2 | Shared | 2 | 4 |  |  |  | Civil lead | TIDP-G | Y | Y | N |  | Real site model; drainage and access
G-201 | Civil and Site |  | 00 | Site and drainage drawings (50%) | Drawing | SH | 2.2 Deliverable B | 300 | PDF/DWG | S2 | Shared | 4 | 4 |  |  |  | Civil lead | TIDP-G | N | Y | N
G-300 | Civil and Site |  | 00 | Civil and site model and drawings (100%) | Model/Drawing | M3 | 2.3 Deliverable C | 350 | RVT/PDF | S4 | Shared | 5 | 8 |  |  |  | Civil lead | TIDP-G | Y | Y | N
G-500 | Civil and Site |  | 00 | Construction-stage model (revisions tracked) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | A1 | Published | 12 | 43 |  |  |  | Civil lead | TIDP-G | Y | Y | N
G-700 | Civil and Site |  | 00 | As-built civil and site model (LOD 500, verified) | Model | M3 | 3.3 Deliverable D | 500 | RVT/IFC | A1 | Published | 48 | 49 |  |  |  | Civil lead | TIDP-G | Y | Y | Y |  | Authored by the design consultant from the Contractor as-built documentation; verified by the Information Manager

## TIDP-Q
Task Information Delivery Plan — Quantity surveying / cost
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-Q
Scope | Quantity surveying / cost
Appointed party | [FILL — quantity surveyor]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
Z-212 | QS / Cost |  | ZZ | Bill of quantities (preliminary) | Schedule | BQ | 2.2 Deliverable B | 300 | XLSX | S2 | Shared | 4 | 4 |  |  |  | Quantity Surveyor | TIDP-Q | Y | N | Y |  | Derived from the coordinated models by the QS
Z-310 | QS / Cost |  | ZZ | Bill of quantities (tender) | Schedule | BQ | 2.3 Deliverable C | 350 | XLSX | S4 | Shared | 8 | 8 |  |  |  | Quantity Surveyor | TIDP-Q | Y | N | Y

## TIDP-FF
Task Information Delivery Plan — FF&E and finishes (Interior Designer)
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-FF
Scope | FF&E and finishes (Interior Designer)
Appointed party | [FILL — interior designer]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
FF-200 | FF&E |  | ZZ | FF&E and finishes register (first Fohlio exchange) | Schedule | SC | 2.2 Deliverable B | 300 | CSV/XLSX | S2 | Shared | 4 | 4 |  |  |  | Interior Designer | TIDP-FF | N | N | Y |  | Matched on room number
FF-300 | FF&E |  | ZZ | FF&E specifications and schedule | Schedule | SC | 2.3 Deliverable C | 350 | XLSX/PDF | S4 | Shared | 8 | 8 |  |  |  | Interior Designer | TIDP-FF | Y | N | Y |  | Reconciled to Fohlio
FF-600 | FF&E |  | ZZ | FF&E final schedule and procurement record | Schedule | SC | 3.2 FF&E | 400 | XLSX | A1 | Published | 44 | 47 |  |  |  | Interior Designer | TIDP-FF | Y | N | Y |  | Reconciled item by item
FF-601 | FF&E |  | ZZ | Installed FF&E and finishes reconciliation report (model vs Fohlio) | Report | RP | 3.2 FF&E | 400 | XLSX/PDF | S2 | Shared | 47 | 47 |  |  |  | Information Manager | TIDP-FF | Y | N | Y |  | No unlinked items; O&M data collected in Fohlio

## TIDP-C
Task Information Delivery Plan — Contractor and specialists
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-C
Scope | Contractor and specialists
Appointed party | [FILL — main contractor]
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
C-500 | Contractor |  | ZZ | Shop drawings and fabrication models (steel, MEP modules, façade) | Model/Drawing | M3 | 3.1 Construction | 400 | RVT/IFC/PDF | S2 | Shared | 12 | 43 |  |  |  | Contractor | TIDP-C | Y | Y | N |  | Linked into the federation
Z-512 | Contractor |  | ZZ | As-built capture (progressive) | Model | M3 | 3.1 Construction | 400 | RVT/IFC | S2 | Shared | 12 | 43 |  |  |  | Contractor | TIDP-C | Y | Y | N |  | Clouded changes in official documentation; current to within one month
Z-513 | Contractor |  | ZZ | Asset data capture (tiered schedule, BEP 14) | Schedule | SC | 3.1 Construction | 400 | XLSX | S2 | Shared | 12 | 47 |  |  |  | Contractor | TIDP-C | Y | Y | Y |  | Tier A serialised plant, B maintainable devices, C warranted fabric
C-700 | Contractor |  | ZZ | Final as-built documentation, commissioning records, warranties and O&M documents | Document | RP | 3.3 Deliverable D | 500 | PDF | A1 | Published | 48 | 48 |  |  |  | Contractor | TIDP-C | Y | Y | Y |  | Input to the record model verification

## TIDP-ALL
Task Information Delivery Plan — Every appointed party
The deliverables below are those already assigned to you in the Master Information Delivery Plan. Confirm the planned dates, add any deliverable your scope requires that is not listed, and return this sheet to the Information Manager. Rows are merged back into the register by reference. Use the drop-down lists; if a value you need is not offered, raise it rather than typing a variant.
Task Information Delivery Plan | TIDP-ALL
Scope | Every appointed party
Appointed party | All parties
Originator code | [FILL — once the register is issued]
Task Team Manager | [FILL]
Contact | [FILL]
Revision | P01
Date | [FILL]
Ref | Discipline | Originator | Volume | Deliverable | Type | Type code | Stage | LOD | Format | Suitability | CDE State | Month from | Month to | Planned date | Actual date | Variance (days) | Responsible | TIDP ref | Critical | As-built | O&M | RAG | Notes
Z-006 | All disciplines |  | ZZ | Task Information Delivery Plan (one per appointed party) | Schedule | SC | Mobilisation | n/a | XLSX | S3 | Shared | 0 | 0 |  |  |  | Task Team Managers | TIDP-ALL | N | N | N |  | Returned to the Information Manager; merged into this MIDP
Z-311 | All disciplines |  | ZZ | Specifications (RIB SpecLink, CSI MasterFormat) | Specification | SP | 2.3 Deliverable C | 350 | PDF | S4 | Shared | 8 | 8 |  |  |  | Task Team Managers | TIDP-ALL | Y | N | Y |  | Issued sets archived with the milestone
Z-705 | All disciplines |  | ZZ | Native design, calculation, energy and system program files (A1 Deliverable D) | Document | RP | 3.3 Deliverable D | 500 | Native | A1 | Published | 48 | 49 |  |  |  | Task Team Managers | TIDP-ALL | Y | N | Y

## Summary
Delivery summary
Calculated from the MIDP sheet. Do not type in this sheet.
By stage
Stage | Deliverables | Complete | Red | Amber | Outstanding
Mobilisation
2.1 Deliverable A
2.2 Deliverable B
2.3 Deliverable C
2.4 Tender
2.5 Conformed set
3.1 Construction
3.2 FF&E
3.3 Deliverable D
Total
By discipline
Discipline | Deliverables | Complete | Red | Amber | Outstanding
Information Management
Architecture
Interiors
Structure
Mechanical
Electrical
Public Health
Fire Protection
Low Voltage
Civil and Site
QS / Cost
FF&E
Contractor
All disciplines
Total
By Task Information Delivery Plan
TIDP | Deliverables | Complete | Red | Amber | Outstanding
TIDP-Z
TIDP-A
TIDP-S
TIDP-M
TIDP-E
TIDP-P
TIDP-FP
TIDP-LV
TIDP-G
TIDP-Q
TIDP-FF
TIDP-C
TIDP-ALL
Total
Deliverable classes
Class | Deliverables
On the critical path
Feeding the as-built model
Feeding the O&M / asset data pack

## Drawing schedule
Planned drawing schedule
Indicative sheet counts by volume and role, carried forward from the June information delivery plan. Confirmed against each Task Information Delivery Plan at mobilisation and rebaselined at Deliverable B.
Volume | Building | Role | Sheets | Content
01 | Temple (2,449 m²) | A | 28 | GA plans, RCPs, elevations, sections, details, door/window schedules
01 | Temple (2,449 m²) | S | 17 | Foundations, framing plans, sections, details, schedules
01 | Temple (2,449 m²) | M | 14 | HVAC plans, schematics, equipment schedules, details
01 | Temple (2,449 m²) | E | 24 | Power, lighting (17 + 7 lighting sheets), single-line, panel schedules, details
01 | Temple (2,449 m²) | P | 11 | Water, drainage, schematics, details
01 | Temple (2,449 m²) | FP | 6 | Fire strategy, sprinkler and detection layout
01 | Temple (2,449 m²) | A (interiors) | 8 | FF&E layouts, finishes, joinery
02 | Meetinghouse (1,312 m²) | A | 20 | GA plans, RCPs, elevations, sections, details, door/window schedules
02 | Meetinghouse (1,312 m²) | S | 12 | Foundations, framing plans, sections, details, schedules
02 | Meetinghouse (1,312 m²) | M | 10 | HVAC plans, schematics, equipment schedules, details
02 | Meetinghouse (1,312 m²) | E | 17 | Power, lighting (12 + 5), single-line, panel schedules, details
02 | Meetinghouse (1,312 m²) | P | 8 | Water, drainage, schematics, details
02 | Meetinghouse (1,312 m²) | FP | 4 | Fire strategy, sprinkler and detection layout
02 | Meetinghouse (1,312 m²) | A (interiors) | 6 | FF&E layouts, finishes, joinery
03 | Housing / ancillary (2,554 m²) | A | 24 | GA plans, RCPs, elevations, sections, details, door/window schedules
03 | Housing / ancillary (2,554 m²) | S | 14 | Foundations, framing plans, sections, details, schedules
03 | Housing / ancillary (2,554 m²) | M | 12 | HVAC plans, schematics, equipment schedules, details
03 | Housing / ancillary (2,554 m²) | E | 20 | Power, lighting (14 + 6), single-line, panel schedules, details
03 | Housing / ancillary (2,554 m²) | P | 10 | Water, drainage, schematics, details
03 | Housing / ancillary (2,554 m²) | FP | 5 | Fire strategy, sprinkler and detection layout
03 | Housing / ancillary (2,554 m²) | A (interiors) | 7 | FF&E layouts, finishes, joinery
04 | Grounds building (93 m²) | A | 7 | GA plans, RCPs, elevations, sections, details
04 | Grounds building (93 m²) | S | 4 | Foundations, framing, sections, details
04 | Grounds building (93 m²) | M | 4 | HVAC plans, schematics, details
04 | Grounds building (93 m²) | E | 4 | Power, lighting, single-line, details
04 | Grounds building (93 m²) | P | 3 | Water, drainage, details
05 | Utility building (166 m²) | A | 9 | GA plans, RCPs, elevations, sections, details
05 | Utility building (166 m²) | S | 5 | Foundations, framing, sections, details
05 | Utility building (166 m²) | M | 4 | HVAC plans, schematics, details
05 | Utility building (166 m²) | E | 7 | Power, lighting (5 + 2), single-line, details
05 | Utility building (166 m²) | P | 4 | Water, drainage, details
05 | Utility building (166 m²) | FP | 2 | Fire strategy, sprinkler and detection layout
05 | Utility building (166 m²) | A (interiors) | 3 | FF&E layouts, finishes
06 | Guard house (23 m²) | A | 4 | GA plans, elevations, sections, details
06 | Guard house (23 m²) | S | 2 | Foundations, framing
06 | Guard house (23 m²) | M | 2 | HVAC plan, details
06 | Guard house (23 m²) | E | 2 | Power and lighting, single-line
06 | Guard house (23 m²) | P | 2 | Water, drainage
00 | Site-wide / external works | G | 4 | Grading and levels
00 | Site-wide / external works | G | 4 | Drainage and stormwater
00 | Site-wide / external works | G | 3 | Utilities and services
00 | Site-wide / external works | G | 2 | Roads, paving and parking
00 | Site-wide / external works | G | 3 | External works and landscape
00 | Site-wide / external works | G | 4 | Civil details and sections
Total sheets

## Change log
Change log
What changed between the previous issue of this register and this one, and why. "Restored" rows were carried by the June plan and dropped by the August issue.
Counts
Change | Deliverables
Carried forward | 78
Restored | 22
Added | 21
Total | 121
Rows added or restored
Ref | Change | Deliverable | Reason
Z-000 | Carried forward | BIM Execution Plan | Reference KUT-SMB-ZZ-ZZ-RP-Z-0001 (I-01)
Z-001 | Carried forward | Master Information Delivery Plan | Type Document → Schedule; reference SC-Z-0001
Z-003 | Carried forward | Responsibility matrix (RACI) | June ref Z-002; reissued with P02 codes
Z-004 | Carried forward | Project template, family library and title blocks | June ref Z-006
Z-005 | Carried forward | Originator code register | Responsible: Appointing Party → Lead Appointed Party (B-02)
Z-007 | Carried forward | Standards reconciliation schedule (BEP 4.1.3) | End month set to M8: closed before Technical Design
Z-012 | Carried forward | CDE folder structure and permission matrix | June ref Z-005 "CDE setup"
Z-018 | Added | Standards localisation note (Owner standards to Ugandan practice) | Added from proposal 4.1 (BEP 4.1.4)
Z-019 | Added | Stage 0 gate record (test model shared by every appointed party) | Added (A-02): the Stage 0 exit gate had no date
Z-020 | Added | Monthly BIM status report (design stage) | Added (D-05): proposal 4.5 requires monthly reporting throughout; Aug MIDP started at M12
Z-021 | Restored | Kickoff induction record and BEP acknowledgement | June ref Z-007 "Kickoff training + signed BEP"; dropped in Aug
Z-022 | Added | Document Control Standard (reissued to P02 codes) | Added (I-02); June document RP-Z-0001 renumbered RP-Z-0003. Absorbs the separate numbering convention (June RP-Z-0004), which would have been a second copy of the naming rules
Z-024 | Restored | Drawing register, transmittal and notice templates | June templates carried; Uniclass column replaced by CSI section (E-05)
Z-010 | Carried forward | Federated coordination model | June ref Z-003
A-101 | Added | Deliverable A drawing set | Added: Playbook 6.1 lists a Deliverable A drawing set that no MIDP carried
G-100 | Carried forward | Site model and levels | Volume 00 (site-wide)
Z-112 | Carried forward | Deliverable A gate pack and compliance report | Compliance report named explicitly (proposal 2.1)
Z-113 | Added | Deliverable A Owner review set and comment close-out report | Added (D-05): bookmarked, hyperlinked review set; two-week Owner review
Z-114 | Added | Baseline model-health report | Added from proposal 4.1 (week 4 baseline audit)
A-202 | Carried forward | Door and window schedules | ISO type SH (schedule) → SC (B-04)
P-201 | Added | Plumbing and drainage layouts (50%) | Added: 50% set for P was missing while the drawing schedule plans P sheets
LV-200 | Added | Low voltage containment and equipment rooms | Added: LV appears in Aug only at Deliverable C
G-200 | Restored | Site model | Restored from June (absent in Aug)
G-201 | Restored | Site and drainage drawings (50%) | Restored from June (absent in Aug)
Z-210 | Carried forward | Coordination reports (fortnightly) and Deliverable B clash close-out | ISO type CR
Z-212 | Carried forward | Bill of quantities (preliminary) | ISO type BQ; measurement standard [FILL] (D-03)
Z-213 | Carried forward | Deliverable B gate pack, LOD 300 verification and compliance report | Verification and compliance report named
Z-214 | Added | Deliverable B Owner review set and comment close-out report | Added (D-05)
A-302 | Added | Room data sheets (complete) | Added: Playbook 6.3 places the RDS set at 2.3
M-300 | Carried forward | Mechanical model | Aug merged model and drawings; split restored
M-302 | Restored | HVAC load and sizing schedules | June ref M-300b restored
M-303 | Added | BMS point-naming convention and point data on serviceable elements | Added (BEP 11.3)
E-301 | Restored | Panel schedules and single-line diagrams | June ref E-300b restored
G-300 | Restored | Civil and site model and drawings (100%) | Restored from June (absent in Aug)
Z-310 | Carried forward | Bill of quantities (tender) | ISO type BQ
Z-311 | Carried forward | Specifications (RIB SpecLink, CSI MasterFormat) | Responsible: Lead AP → each discipline authors (RACI C12)
Z-314 | Added | Deliverable C Owner review set and comment close-out report | Added (D-05)
Z-410 | Carried forward | Conformed set | June ref Z-401
Z-411 | Added | Conformed-set conformance audit and compliance report | Added (D-05): the conformed set is one of the five contractual gates
A-500 | Restored | Construction-stage model (revisions tracked) | Per-discipline rows restored; Aug collapsed them into ALL-500 (G-02)
S-500 | Restored | Construction-stage model (revisions tracked) | Per-discipline rows restored; Aug collapsed them into ALL-500 (G-02)
M-500 | Restored | Construction-stage model (revisions tracked) | Per-discipline rows restored; Aug collapsed them into ALL-500 (G-02)
E-500 | Restored | Construction-stage model (revisions tracked) | Per-discipline rows restored; Aug collapsed them into ALL-500 (G-02)
P-500 | Restored | Construction-stage model (revisions tracked) | Per-discipline rows restored; Aug collapsed them into ALL-500 (G-02)
FP-500 | Restored | Construction-stage model (revisions tracked) | Per-discipline rows restored; Aug collapsed them into ALL-500 (G-02)
LV-500 | Restored | Construction-stage model (revisions tracked) | Per-discipline rows restored; Aug collapsed them into ALL-500 (G-02)
G-500 | Restored | Construction-stage model (revisions tracked) | Per-discipline rows restored; Aug collapsed them into ALL-500 (G-02)
C-500 | Added | Shop drawings and fabrication models (steel, MEP modules, façade) | Added (Playbook 6.6; risk "late specialist models")
Z-511 | Carried forward | Monthly BIM status report (construction) | End month M43 → M49: reporting continues through 3.2 and 3.3
Z-513 | Carried forward | Asset data capture (tiered schedule, BEP 14) | End month M43 → M47: capture continues through FF&E installation
Z-514 | Carried forward | Asset data completeness report (monthly, by tier and volume) | End month M43 → M47
Z-515 | Restored | Quarterly model-health audit | June ref Z-514 restored; required by proposal 2.1 and 4.5
Z-516 | Restored | Revision register | June ref Z-512 restored
Z-517 | Added | Contractor and specialist induction record | Added (proposal 2.1; BEP 12)
Z-518 | Added | Construction-stage coordination reports (monthly) | Added: monthly federation and clash in construction (BEP 7.1)
FF-600 | Carried forward | FF&E final schedule and procurement record | Month M43 → M44–M47 (A-01)
FF-601 | Added | Installed FF&E and finishes reconciliation report (model vs Fohlio) | Added (Playbook 6.7 exit criteria)
A-700 | Carried forward | As-built architectural model (LOD 500, verified) | Month M45 → M48–M49 (A-01)
S-700 | Carried forward | As-built structural model (LOD 500, verified) | Month M45 → M48–M49 (A-01)
M-700 | Carried forward | As-built mechanical model (LOD 500, verified) | Month M45 → M48–M49 (A-01)
E-700 | Restored | As-built electrical model (LOD 500, verified) | Month M45 → M48–M49 (A-01); per-discipline row restored (G-02)
P-700 | Restored | As-built plumbing and drainage model (LOD 500, verified) | Month M45 → M48–M49 (A-01); per-discipline row restored (G-02)
FP-700 | Restored | As-built fire protection model (LOD 500, verified) | Month M45 → M48–M49 (A-01); per-discipline row restored (G-02)
LV-700 | Restored | As-built low voltage model (LOD 500, verified) | Month M45 → M48–M49 (A-01); per-discipline row restored (G-02)
G-700 | Restored | As-built civil and site model (LOD 500, verified) | Month M45 → M48–M49 (A-01); per-discipline row restored (G-02)
C-700 | Added | Final as-built documentation, commissioning records, warranties and O&M documents | Added (A1: within 60 days of substantial completion)
Z-700 | Carried forward | COBie 2.4 handover dataset — CONDITIONAL on Owner instruction | Marked conditional (D-01): excluded from the base services in proposal 2.2
Z-701 | Carried forward | Operation and maintenance / asset data pack (Fohlio) | Month M45 → M48–M49
Z-702 | Carried forward | Reconciled building management system point register (digital-twin baseline) | Month M45 → M49
Z-703 | Carried forward | Deliverable D gate pack: LOD 500 verification and asset data completeness | Month M45 → M49
Z-704 | Carried forward | Final transmittal and project archive | June ref Z-703; ISO type TR
Z-705 | Added | Native design, calculation, energy and system program files (A1 Deliverable D) | Added (A1 Deliverable D contents; proposal 4.4 days 35 to 50)
Z-706 | Added | Final drawing register | Added (Playbook 6.8 deliverables)
Retired references
Ref | From | Deliverable | Disposition
Z-023 | New P02 | Drawing and document numbering convention (reissued) | Absorbed into Z-022, the Document Control Standard. A separate numbering convention would have been a third statement of the container naming rules, beside BEP 4.2 and the standard itself, and the June pair had already drifted apart
ALL-500 | Aug P01 | Construction stage models (all disciplines) | Replaced by per-discipline rows A-500 to G-500 (G-02)
Z-004 (June) | Jun P01 | Naming and tagging standard | Merged into BEP 4.2 and Playbook s4; no separate document
Z-005 (June) | Jun P01 | CDE setup (four states + permissions) | Became Z-012 CDE folder structure and permission matrix
Z-006 (June) | Jun P01 | Revit template + controlled family library | Became Z-004
Z-007 (June) | Jun P01 | Kickoff training + signed BEP | Became Z-021
Z-003 (June) | Jun P01 | Federated coordination model at 2.1 | Kept as Aug ref Z-010
Z-401 (June) | Jun P01 | Conformed set | Kept as Aug ref Z-410
Z-512 (June) | Jun P01 | Revision register | Became Z-516 (Aug Z-512 is the Contractor as-built capture row)
Z-514 (June) | Jun P01 | Quarterly model-health audit | Became Z-515 (Aug Z-514 is the asset data completeness report)
M-300b / E-300b (June) | Jun P01 | HVAC load schedules; panel schedules and single-line diagrams | Became M-302 and E-301
Z-703 (June) | Jun P01 | Final handover transmittal + archive | Became Z-704 (Aug Z-703 is the Deliverable D gate pack)

## Lists
Discipline | Originator | Type | Stage | LOD | Suitability | CDE State | RAG | Volume | Type code | Yes/No
Information Management | [FILL — from the originator code register] | Model | Mobilisation | n/a | S0 | WIP | Green | 00 | M3 | Y
Architecture |  | Drawing | 2.1 Deliverable A | 100 | S1 | Shared | Amber | 01 | M2 | N
Interiors |  | Schedule | 2.2 Deliverable B | 200 | S2 | Published | Red | 02 | DR
Structure |  | Document | 2.3 Deliverable C | 300 | S3 | Archived | Complete | 03 | SH
Mechanical |  | Specification | 2.4 Tender | 350 | S4 |  |  | 04 | SC
Electrical |  | Report | 2.5 Conformed set | 400 | A1 |  |  | 05 | SP
Public Health |  | Calculation | 3.1 Construction | 500 | B1 |  |  | 06 | RP
Fire Protection |  | Room data sheet | 3.2 FF&E |  |  |  |  | ZZ | CA
Low Voltage |  | Model/Drawing | 3.3 Deliverable D | [5 empty] | RD
Civil and Site |  | Model/Document | [6 empty] | MS
QS / Cost |  | Schedule/Drawing | [6 empty] | PP
FF&E | [8 empty] | CR
Contractor | [8 empty] | TR
All disciplines | [8 empty] | BQ
Reference prefix | Groups | Container role code
A | Architecture and interiors | A
S | Structure | S
M | Mechanical | M
E | Electrical, including lighting | E
P | Public health | P
FP | Fire protection | FP
LV | Low voltage and communications | LV
G | Civil and site | G
FF | FF&E and finishes | A — issued under architecture
C | Contractor and specialists | per the discipline of the container
Z | Information management, cost and project-wide | Z